## Sheet1
ID | Story | Sprint | Story Priority | Story Status | Story Points
8 | As a student user I would like to be able to post listings so that I can find a tutor. | 1 | H | W | 2
13 | As a student user I need to have a customizable student profile so that I can add basic information about me and what my interests are. | 1 | H | W | 3
21 | As a tutor user I would like to have a profile to showcase why I should be hired. | 1 | H | W | 3
23 | As a tutor user I need to be able to set my pay rate for what I offer, so that students are aware of this payment condition. | 1 | H | W | 1
1 | As a general user I need to be able to search any user by their public username so that I can view their profile. | 2 | H | W | 1
9 | As a student user I would like to have access to tutors profiles so I can decide who to hire. | 2 | H | W | 2
16 | As a prospecting tutor I would like to apply to become a tutor so that I can start applying to jobs. | 2 | H | W | 2
17 | As a tutor user I would like to respond to listings so that I can be hired. | 2 | H | W | 3
36 | As a manager of the application I would like to be able to compare time spent on subjects to see which areas need more tutors in. | 2 | H | W | 2
37 | As a manager of the application I would like to be able to kick/ban users for misusing the app (ex. Cheating on class materials) | 2 | H | W | 2
0 | As a general user I would like to have a login so that my account is secure. | 3 | H | W | 3
5 | As a general user I would like to have a toolbar to access the various applications features. | 1 | M | W | 2
35 | As a manager of the application I would like to have a feature to see all of the tutors currently associated with a student and those who are not commissioned yet. | 1 | M | W | 1
6 | As a general user I would like the application to be organized effectively to increase productivity. | 2 | M | W | 3
7 | As a general user I would like the main features to be easily accessible compared to less important features, as I will be using the main features the most. | 2 | M | W | 2
2 | As a general user I would like to PM other users so that we can connect. | 3 | M | W | 3
14 | As a student user I want to be able to message my tutor so that any of my questions can be asked to my tutor even when we are not in a session. | 3 | M | W | 1
25 | As a tutor user I need to be able to message and talk to my students so we can communicate our needs. | 3 | M | W | 3
26 | As a tutor user I need to have a means of communicating with application managers so that emergencies can be handled properly. | 3 | M | W | 1
30 | As a tutor user I would like a portal to send extra practice/homework to students so that they can succeed in courses. | 3 | M | W | 2
11 | As a student user I would like to have a tool to compare schedules with my tutor. | 4 | M | W | 3
22 | As a tutor user I would like to have a place to upload letters of recommendation to increase likelihood of being hired. | 4 | M | W | 1
4 | As a general user I need to have available various forms of contact from the app team so that I can ask for assistance. | 3 | L | W | 1
10 | As a student user I would like to be able to connect with tutees in similar subjects so that we can form study groups. | 4 | L | W | 1
15 | As a student user I would like to have a portal to update my tutor with recent grades so that they know where I stand academically. | 4 | L | W | 2
29 | As a tutor user I would like to have access to resources for tutoring practices to best tutor students. | 4 | L | W | 1
32 | As a manager of the application I would like to have weekly reports on users so that I know the level that this application is being used at. | 4 | L | W | 2
33 | As a manager of the application I would like to have data on the amount of missed sessions and completed sessions to track issues with session planning. | 4 | L | W | 2
3 | As a general user I would like to be sent emails so that I can stay updated. | 5 | L | W | 1
12 | As a student user I need to be able to search for tutors by subject so that I can find a good fit for my area of interest. | 5 | L | W | 2
18 | As a tutor user I would like to receive an email when new jobs are listed to increase my likelihood of being hired. | 5 | L | W | 2
28 | As a tutor user I need to be able to send reminder emails to tutee’s about upcoming tutor appointments. | 5 | L | W | 1
34 | As a manager of the application I would like to have a feedback response on many of the features offered to help with ease of user management. | 5 | L | W | 2
19 | As a tutor user I would like to be given tutor history on students so that I know their learning style. | 6 | L | W | 2
20 | As a tutor I would like to rate the student or leave feedback for other tutors to see | 6 | L | W | 1
24 | As a tutor user I need to be able to set up a direct deposit so that I can receive my payment. | 6 | L | W | 3
27 | As a tutor user I need to be able to video chat with my students for virtual tutoring sessions. | 6 | L | W | 3
31 | As a tutor user I would like to be able to see what other tutors are doing in their private sessions and the impact of what they are doing. | 6 | L | W | 1